## Sheet1
Streamlining and Waste Reduction Kaizen: Example Agenda
Day 1
Time | Session Description | Deliverables/Outputs | LSS Tools | Required Participants
Start-End Times
(10 minutes) | Welcome and introduction | Understood purpose, scope, and agenda | Kaizen project charter | Welcome by champion and review of agenda by facilitator. All participants: process owners and selected operators of process ABC, and SMEs
(30 minutes) | Walk the process | Spaghetti diagram | Gemba, spaghetti diagram, waste identification (TIMWOODS) | Process owners and selected operators of process ABC, and SMEs
(1 hour, 30 minutes) | Map and understand the current "as is" state of process ABC | Current state high-level process map; detailed process map(s) | High-level, process decomposition, detailed process mapping (as appropriate) | Process owners and selected operators of process ABC, and SMEs
(15 minutes) | Morning break
(1 hour) | Analyze process ABC | List of improvement opportunities | VA/NVA/BVA analysis, cycle time and bottleneck analysis, 5 Whys | Process owners and selected operators of process ABC, and SMEs
(1 hour) | Lunch
(30 minutes) | Generate ideas and potential solutions | List of improvement ideas and potential solutions | Brainstorming, affinity diagrams | Process owners and selected operators of process ABC, and SMEs
(30 minutes) | Evaluate and select solutions | List of actionable recommendations | Multi-voting, effort/impact matrix, criteria selection matrix, SMART | Process owners and selected operators of process ABC, and SMEs
(30 minutes) | Map the "to be" future-state improved process ABC | Future state high-level value stream map and supporting detailed process map(s) | Value stream mapping and detailed swim lane process mapping (as appropriate) | Process owners and selected operators of process ABC, and SMEs
(10 minutes) | Provide feedback for day 1 | Pluses and deltas on flip chart | Sticky notes (one plus or delta on each note) | Process owners and selected operators of process ABC, and SMEs
Day 2*
Time | Session Description | Deliverables/Outputs | LSS Tools | Required Participants
Start-End Times
(10 minutes) | Recap of day 1 | Review of deliverables from day 1
(2 hours) | Identify and mitigate potential risks of failure | Process FMEA | FMEA | Process owners and selected operators of process ABC, and SMEs
(15 minutes) | Morning break
(1.5 hours) | Develop process control plan | Process control plan | Process control plan | Process owners and selected operators of process ABC, and SMEs
(1 hour) | Lunch
(2 hours) | Develop standard work procedures | Standard work | Standard work | Process owners and selected operators of process ABC, and SMEs
(10 minutes) | Kaizen event feedback | Pluses and deltas on flip chart | Sticky notes (one plus or delta on each note) | Process owners and selected operators of process ABC, and SMEs
(15 minutes) | Afternoon break
(30 minutes) | Develop implementation plan | Plan for implementing actionable recommendations (with timeline and resources listed) | Project planning | Process owners and SMEs
(1 hour) | Prepare event report | Event report/presentation | Flip charts, PowerPoint | Facilitator and process owners
(30 minutes) | Present report to management | Approval for implementation | Presentation and Q&A | Champion and other senior managers
*Times for process mapping, FMEA, control plans and standard work can vary depending on the length and complexity of the process. The Kaizen may last as long as 4 or 5 days.